## Slide 1
GCC Meeting
NORDUnet office
1-2 October 2025
Slides- Dawn
Restricted

## Slide 2: Innovation Programme
IP launch-1 October
Current max 50K- CONSIDER higher threshold (DRE impact at 300K)??
Promotion-1 Oct-1 Nov SPREAD THE WORD VIA YOUR NREN and NETWORK
Deadline- 14 Nov 12:00 CET
SME list- Requests sent, any other names to add?
Sub-committee review- first cut Ivana and Erik 17-21 Nov (earlier possible??)
SME review (indico) 24 Nov-5 Dec
GCC full review for final selection?? Mtg 8 Dec, 15-17:00 CET
Final decision- week of 8 Dec (communication to recipients, CONNECT announcement)
Contracting- before 31 Dec
Project period- Jan-Jun 2026, TNC included

## Slide 3: GÉANT Strategy Update
Strategy main components under review (Board and GA)
Services and Engagement Substrategies starting point- input at SIG-MSP, CTO workshop
Substrategies completed by January for Feb Board review
Pre-approval at March GA
Final approval and launch at TNC26

## Slide 4: GÉANT Association Strategy Development Timeline
Jan 2025 Exec Retreat
Feb 2025 Board Meeting (agree process)
Mar 2025 GA input
Jun 2025
GA Update
Jul 2025 Board/Exec Retreat- Draft 1
Nov 2025
CTO Workshop consultation
GA Check In/Validation
Dec 2025
Feedback collated
Mar 2026 GA First Approval/Final edits
Jun 2026
GA Approval/ Launch
Apr/May 2025
All staff, community & external stakeholder input
May 2025 Board Update
Sept 2025
All-hands consultation
GA virtual update
Board update
Jan 2026
Exec retreat- Draft 2
Feb 2026 Board Meeting (final input/ recommendation to Board)
Apr 2026
Final draft
May 2026
Submit to GA
Oct 2025
Board update
Prep CTO Workshop
LISTEN
SYNTHESIZE, FORMULATE, CONSULT, ITERATE
LAUNCH
Governance meeting
Input/consultation​
Drafts
Notes: Narrative by Oct Board meeting
CTO workshops- breakout groups, targeted questions, input for sub-goals
Dec- Exec develop sub-goals
Jan Exec retreat- subgoals finalised for Feb Board mtg

## Slide 5: Strategy Development-Vision and Mission
Vision
Powering knowledge for Europe
Mission
Guarantee platforms for digital infrastructure and services that accelerate research, education, and innovation for a secure and competitive Europe.

## Slide 6: Strategy Development-Priorities
Priorities
  Act as One for impactful Research and Education.
  Strengthen networks across Europe and beyond.
  Build a sustainable financial model for the future of our community.
  Lead with a service-driven approach that supports scalable solutions.

## Slide 7: Strategy Development-Uncertainties and Transformations
Uncertainties:
  Geopolitical uncertainty with the risk of fragmentation.
  A diverse GÉANT community with a spectrum of needs.
  An evolving EU regulatory environment​.
  Our service portfolio must remain relevant and essential to our members and users.
  Transformations:
  Facilitate and enable strong NREN collaboration.​
  Develop and deliver a relevant value proposition. ​
  Ensure organisational resilience through a sustainable business model. ​
  Establish and execute a common vision on services and innovation across Europe and globally.​
  Deliver a solid multiplier effect on EU and European investment. ​
  Leverage our unique position in Europe to increase visibility and influence policy. ​

## Slide 8: Service Delivery and Development Sub-strategy
Goal areas:
Network Quality & Reach
Pan-European AAI Layer
High‑Value Community Products & Services
R&E Innovation & Emerging Tech
Unified Security Strategy
Education as a Priority
Work in progress

## Slide 9: Engagement Sub-strategy
Goal areas:
Trusted Partner to an Engaged Membership
New Users via New Business Lines
Member Diversity as an Opportunity
Consistent Services Marketing & Brand Unification
Recognised R&E Influencer
New Partnerships
Support Global R&E
Work in progress

## Slide 10: SIG update
2025
SIG-DHD hanging on, new SC Chair. Final chance 2026
No more TRANSITS
SIG-CISS/DHD coordinator opening
Unassigned mtgs:
SIG-CNaaS: 10 Nov, Utrecht
2026
SIG-MSP/SIG-Marcomms: March, Lisbon
SIG-Quantum/SIG-TFN: Feb/March, Paris
SIG-NOC: TBD, most likely April
SIG-ISM: Security Days, Utrecht
SIG-AI: Mar/Apr, Madrid (backup SIKT)
SIG-Sustainability- Mar/Apr, webinar re: sustainability reporting- other SIG interest?
SIG-NGN: ?
TF-EDU: TNC
SIG-RED: TNC?
SIG-Procurement: TNC?
GCP workshop: when?

## Slide 11: GCP check-in
20 Nov, 14-16:00 CET (virtual)
Agenda items:
  GCP developments
  Fall meeting updates
  Upcoming spring meetings, synergies & cross collaboration
  NON SIG activities?
  TNC26 Community Hub ideas, promotion (4 Feb call for proposals open)
  Sustainability ideas
  Standards list- still of interest?

## Slide 12
Thank You
Any questions?
www.geant.org